## Sheet1
IPAC Paving Limited
Unit 8 – Suite 872, 9251 Yonge St
Richmond Hill, ON L4C 9T3
Project Name: |  |  | PO Date:
Project Address: |  |  | PO #
|  |  | Payment Terms: |  | net 30
Attention To: |  | IPAC PAVING LTD. | Contact Person: |  | Ruslan Klochko
|  | 7100 Fir Tree Drive, Richmond Hill, ON L5S 1G5 |  | Cell# | 647-904-0290
|  |  |  | Email: | ruslan@ipacpaving.com
Qty | Unit | Description |  |  | Unit Price | Contract Price
1 | Quantity | Median Barrier 4m (13.12ft) - I LOCK Connection |  |  | $8.99 | $28,970.10
[5 empty] | Subtotal: | $28,970.10
HST 13%
Total:
Date Required: |  | Please contact John Corbo:
(416) 993-2116
NOTES:
** Quantity take off and specs is the responsibility of the subcontractor and MUST be in accordance with the drawings and the most recent addendum
**Submission of shop drawings within 3 days from PO date if applicable
**In the event of any conflict between the terms of this PO and the Quote, this PO shall govern.
1 - CONSTRUCTION SCHEDULE 1.01 The Subcontractor will perform the Work: a) in accordance with a schedule that the Contractor encloses with the Subcontract; or b) if the schedule is provided afterwards, in accordance with a schedule mutually agreed upon. The Subcontractor shall be deemed to have agreed to a subsequently provided schedule, if the Subcontractor does not object to it in writing within 10 days of its receipt; or c) if no schedule is provided by the Contractor, then starting on or about 3 days after the PO sign and substantially completing the Work, on or about 1 week before. 1.02 The Contractor may, for any reason, reasonably adjust any schedule or specified timing during the course of the Project after consulting with the Subcontractor. 1.03 In case of delay caused by circumstances beyond the control of the Contractor, it may suspend the Subcontractor's performance of the Subcontract in whole or in part. The Contractor may then call upon the Subcontractor to resume performance at any subsequent time and the Subcontractor shall do so, and execute the balance of its obligations. The Contractor shall not be liable to the Subcontractor for any damages or costs that the Subcontractor suffers or incurs because of the suspension or resulting delay. However, the time to complete the Work shall be extended by the period during which it was inactive due to the suspension of Work or by whatever lesser time as would be reasonable in the circumstances. A liquidation damage for any delay affect completion and to achieve Substantial Performance with $500 2 - PAYMENT 2.01 Subject to applicable lien legislation, maintenance/warranty holdbacks, if any, and the provisions of the Subcontract, the Contractor shall make progress payments to the Subcontractor on account of the Subcontract Price. Additionally, a ten percent deficiency holdback will be retained for the duration of the work of this contract and will only be released progressively as deficiencies are rectified and approved by the consultant. The Contractor need not make a progress payment: (a) until the Consultant has certified that the Subcontractor has completed the portion of the Work claimed in the progress application; (b) if a Sub-subcontractor has notified the Contractor that the Sub-subcontractor is claiming against the Contractor for monies the Subcontractor owes for the Sub-subcontractor`s work on the Project. The Contractor need not make the payment for as long as the claim is still outstanding; (c) until the Subcontractor has delivered an executed copy of the Subcontract to the Contractor; and (d) until the Subcontractor has delivered proof that it has complied with the insurance provisions contained in the Subcontract. 2.02 The Subcontractor shall submit a schedule of values of the various parts of the Work to facilitate the evaluation of each application for payment. The sum of the values shall be the Subcontract Price. The schedule shall be submitted to the Contractor as soon as possible, but prior to the first application for payment. 2.03 To make application for payment, the Subcontractor must submit all invoices for work done in the current month, together with current and clear WSIB certificates, insurance documentation in accordance with Article 7, the documents set out in section 8.05, supporting statutory declarations, and other documents that the Contractor requires, no later than 5 days prior to the end of the current month. The application shall cover the value for that part of the Work that the Subcontractor has performed up to the last day of the current month. It must be in accordance with the schedule of values. 2.04 If the Contractor, or the Consultant, makes any changes to any amount in a payment application, the Contractor shall promptly notify the Subcontractor, orally or in writing, of the reasons. The Contractor shall give the Subcontractor the opportunity to defend the submission. 2.05 Subject to the provisions in article 2 and, in particular, to the Subcontractor's obligations in them and subject to applicable construction lien and maintenance holdbacks, payment resulting from each payment application shall be made within 45-60 days from the day of confirmation of progress 2.06 Subject to the provisions in article 2 and, in particular, to the Subcontractor's obligations in them and upon the Subcontractor submitting current and clear WSIB certificates, supporting statutory declarations, and other documents that the Contractor requires, the Contractor shall pay holdback monies in accordance with applicable lien legislation, the Specifications, and the Prime Contract. 2.07 The release of holdback monies shall not be due until authorized by the Consultant’s certificate and until: (a) the expiration of all rights to claim for lien arising from the performance of the Work; (b) 10 days after the issue of the certificate; and (c) the number of days stipulated in the Specifications when holdback monies may be released after the issue of the certificate. . 2.08 Notwithstanding sections 2.01 to 2.07 inclusive, if there are any items of the Work that the Subcontractor cannot readily perform, the Contractor may withhold from payments made on the Subcontract Price until the remaining items are finished. The Contractor may withhold those monies that the Contractor determines are sufficient and reasonable to cover the cost of performing the remaining Work and to adequately protect the Contractor from claims. 2.9 The Contractor may set off, against any money it owes to the Subcontractor, any money that the Subcontractor owes to the Contractor or any damages, liquidated or not, for which the Subcontractor is responsible to the Contractor, whether the monies owing or the damages arise out of the Agreement or any other agreement between the parties.
3 - CHANGES IN THE WORK 3.01 The Contractor, without invalidating the Subcontract, may make changes by altering, adding to or deducting from the Work and the Subcontract Price and subcontract time for the completion of the Work shall be adjusted accordingly in accordance with the provisions of the Prime Contract 3.02 No change shall be made without a written order from the Contractor. 4 - INSURANCE 4.01 The Subcontractor shall provide, maintain and pay for general liability insurance, automobile liability insurance, aircraft and watercraft liability insurance, and any other insurance specified in the Prime Contract, other than property insurance. The amounts of the insurance coverage for the Subcontractor shall be commercially reasonable, but at least as much as described in the Prime Contract. 4.02 Unless specified otherwise in the Prime Contract, the duration of each insurance policy shall be from the date of commencement of the Work until the date of the final certificate for payment of the Prime Contract. The Contractor shall be shown as additionally insured on each policy as it affects the Project. The policies shall be endorsed with the insurer's undertaking to provide the Contractor with not less than thirty (30) days written notice in advance of cancellation, change, or amendment restricting coverage. 4.03 Before the first application for payment of the Subcontract Price, the Subcontractor must supply the Contractor with certificates of insurance, or the actual policy if the Contractor so requests, showing compliance with this article. 4.04 Either the Contractor or the owner will arrange for and maintain property insurance in accordance with the Prime Contract. If the Subcontractor, or any of its Sub-subcontractors, causes a loss that is insured under the property insurance policy, the Subcontractor shall only be responsible to pay for any deductible amounts under the policy. 4.05 The Subcontractor shall be responsible for securing its own tools, equipment, and, until they have been incorporated into the Project, building materials against any eventuality, including theft and vandalism. The Contractor shall not be responsible for any loss to them, whether caused by the negligence of the Contractor or otherwise. The Subcontractor shall obtain appropriate insurance to insure this risk. 5 - CLEAN-UP AND SAFETY 5.01 The Subcontractor shall, at its own expense and to the satisfaction of the Contractor, keep its work areas in a tidy condition and free from the accumulation of waste products and debris. It shall remove from the Project all waste products and debris caused by the performance of the Work. Should it fail to perform these housekeeping requirements, the Contractor shall have the right to have the Work performed by whatever means may be expedient and the Subcontractor agrees to pay all costs of the clean-up and removal of the waste products and debris immediately upon being invoiced for them. **Notwithstanding anything that may be said to you, or allegedly agreed upon between you and IPAC Paving Limited, no amendments to the Subcontract and no subsequent or prior collateral contracts dealing with any portion of the Work, or any other work at the Project, will be valid or enforceable unless executed in writing by IPAC Paving Limited. In particular, any quotation that you may have previously issued has been incorporated, with or without amendments, into this Subcontract and has no further effect. No monies on account of the Subcontract Price that otherwise would be due and owing to you pursuant to the Subcontract will be paid to you until 5 days after you have executed and delivered the duplicate of the Subcontract to us, even if you have commenced the Work and even though the Subcontract is binding on both you and us.
 | Items Reviewed |  |  | Date Submitted to IPAC Office: |  | IPAC Purpose Only: Reviewed date & approved by:
- Certificate of Insurance - Naming General Contractor/Builder as an additional insured, -Includes the Project Name on the certificate -Validity period
Current WSIB Clearance Certificate (if applicable) or letter from WSIB confirming exemption.
Current Health and Safety Policy, signed and dated by most senior person(s).
Current Violence and Harassment Policy by most senior person(s)
Current Health and Safety Programs related to scope of work complying with legislation and maintaining a co-operative, safe worksite.
Any additional required sign-off requirements as per contract/agreement
Current workers training certificates must be send to IPAC prior starting work.
Fully completed Form 1000
List of your Subcontractors/Contractors that are being included for work tasks at the project site (NOTE: Form 1000 and list of these documents to also be provided to IPAC)
Site Supervisor and Worker Health & Safety Representative to be identified
Valid Training Certificates for those anticipated for the project, proof Records of Training (i.e. WHMIS, Fall Protection, MOL Worker Awareness, Recognized License relevant to trade, traffic controller, etc.…)
A complete list of equipment required or anticipated for the project must be present on site
Valid Safety Data Sheets (SDS)
Engineered drawings related to safety procedures (i.e. Static Lines, Scaffolding, Hoisting etc.…)
Other (please explain):
Subcontractors that do not have a health and safety policies, procedures, practices, and/or has a system in place which does not meet the minimum requirement must follow IPAC Paving Inc. health and safety program.
IPAC will evaluate Subcontractors safety performs upon completion of the project.
TERMS AND CONDITIONS OF THIS PURCHASE ORDER:
1. Purchase order number noted above must be indicated on all correspondence and invoicing. 2. An incorrect or missing purchase order may cause a delay in processing system. 3. Deliver no goods without a purchase order. 4. Acknowledge receipt of this purchase order specifying prices and a definite shipping date. 5. Make no substitutions or changes without authority from IPAC Paving Limited 6. IPAC Paving Limited reserves the right to cancel this order if shipment is not made as promised. 7. In addition to the statutory construction lien act holdback and any warranty holdback (if applicable) a ten percent deficiency holdback for contracts below one hundred thousand and a five percent deficiency holdback for contracts above one hundred thousand, will be retained for the duration of the work of this contract and will only be released progressively as deficiencies are rectified and approved by the consultant. 8. This order must not be billed at higher prices than quoted. 9. The documentation noted in this purchase order must be provided and/or filled out and returned to IPAC Paving Limited prior to the commencement of any work or delivery of goods 10. This purchase order supersedes all previous quotes, pricing and negotiations. 11. No payment will be made, unless we receive a signed copy of this P.O and all other documents required thereof 12. Please note that whether or not you sign this document, your arrival on site will be taken as an agreement to abide by the terms and conditions set out in this Purchase Order.
ACCEPTED: |  |  | CONFIRMED:
Company Name:
Buyer: IPAC Paving Limited |  |  | Authorized Person:
Signature
Unit 8 – Suite 872, 9251 Yonge St, Richmond Hill, ON L4C 9T3
Date of Acceptance: